## Risk Management Plan
| Date | 2022-12-09
None
Priority | PROJECT RISK MANAGEMENT PLAN | [25 empty] | WBS 100 Project Management
| Identification | [5 empty] | Qualitative Analysis | [9 empty] | Quantitative Analysis |  |  |  | Response Strategy |  |  | Monitoring and Control |  |  | WBS 150 Develop Project Initiation Document (PID)
| Status | ID # | Date Identified Project Phase | Functional Assignment | Threat | Risk Trigger (Event) Description | Type | Probability | Impact | Risk Matrix | [7 empty] | Probability (%) | Impact (days) | Effect (days) | Strategy | Response Actions including advantages and disadvantages | Affected WBS Tasks | Responsibilty (Task Manager) | Status Interval or Milestone Check | Date, Status or Review Comments | WBS 160 Perform Preliminary Engineering Studies and Prepare Draft Project Report
| Active |  | PID |  |  |  | Scope | Very High | Very High | [8 empty] | 0.9 |  |  | Avoidance | [5 empty] | WBS 165 Perform Environmental Studies and Prepare Draft Environmental Document (DED)
| Dormant |  | PA&ED |  |  |  | Schedule | High | High | [8 empty] | 0.7 |  |  | Transference | [5 empty] | WBS 175 Circulate Draft Environmental Document and Select Preferred Project Alternative
| Retired |  | PS&E |  |  |  | Cost | Moderate | Moderate | [8 empty] | 0.5 |  |  | Mitigation | [5 empty] | WBS 180 Prepare and Approve Project Report and Final Environmental Document
|  |  | Construction |  |  |  | Quality | Low | Low | [8 empty] | 0.3 |  |  | Acceptance | [5 empty] | WBS 185 Prepare Base Maps and Plan Sheets
[8 empty] | Very Low | Very Low | [8 empty] | 0.1 |  |  | N/A | [5 empty] | WBS 190 Prepare Structure Site Plans
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | [6 empty] | (12) |  | (13) | (14) =(13)x(12) | (15) | (16) | (17) | (18) | (19) | (20) | WBS 195 Right of Way Property Management and Excess Land
1 | Active | F1R1 | Sprint 1 | Research | Modification of the project requirements | Missunderstanding between the teachers who proposed the project | Scope | Low | High | Probability | VH | [5 empty] | #REF! | 5% | 14 | 7 | Mitigation | Researching the new requirments and implementing them | WBS 185 Prepare Base Maps and Plan Sheets | Whole team | 4 weeks | Not passed | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | #REF!
[11 empty] | M | [5 empty] | #REF!
(4): All phases | L |  |  |  | X |  | #REF! | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | #REF! | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
2 | Active | F1R2 | Sprint 1 | Research | The time to execute a task takes too long | The found solution during the research stage might not be the most optimal one in our circumstances | Quality | Low | Moderate | Probability | VH | [5 empty] | #REF! | 20% | 14 | 2.8 | Mitigation | Tryng to optimize it as much as possible without exceeding the deadline | WBS 190 Prepare Structure Site Plans | Developers | 2 weeks | Not passed | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | #REF!
[11 empty] | M | [5 empty] | #REF!
(4): All phases | L |  |  | X |  |  | #REF! | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | #REF! | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package | bar: (1) to Very Low (11)
3 | Active | F2R1 | Sprint 2 | Research | Finding a mistake during development in the sources used for research | The documentation used in researching might not be 100% up to date | Scope | Very Low | Low | Probability | VH | [5 empty] | 0 | 15% | 7 | 1.05 | Mitigation | Consulting again more sources before taking action | WBS 230 Prepare Draft PS&E | Developers | 2 weeks | Passed | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
(4): Development | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL |  | X |  |  |  | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
4 | Active | F2R2 | Sprint 2 | Development | Bugs | Errors or the product doesn't work the way it was expected | Scope | Very High | Very High | Probability | VH |  |  |  |  | X | 0 | 100% | 28 | 28 | Mitigation | The testers finding all the possible bugs and distributing them to the development team to solve them | WBS 185 Prepare Base Maps and Plan Sheets | Testers, developers | 2 weeks | Not passed | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
(4): Development | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
5 | Active | F3R1 | Sprint 1 | Development | Some blocks of code might not be compatible together | Integrating the code of each programmer | Quality | Low | Low | Probability | VH | [5 empty] | 0 | 10% | 14 | 1.4 | Mitigation | Fixing the code | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Developers | 2 weeks | Passed(for the current milestone) | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
(4): Development | L |  | X |  |  |  | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
6 | Active | F3R2 | Sprint 2 | development | The performance of the product might be affected by old code in the following stages of the development | Poor code quality | Quality | Very Low | Moderate | Probability | VH | [5 empty] | 0 | 5% | 14 | 0.7 | Acceptance | To not exceed the deadline, for now we might accept the worse quality | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Developers | 2 weeks | Passed
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
(4): Development | L | [5 empty] | 0
[11 empty] | VL |  |  | X |  |  | 0
[12 empty] | VL | L | M | H | VH
Impact
7 | Retired | F3R3 | Sprint 2 | Product management | Having to postpone the launching | Bad time estimation | Schedule | High | Very High | Probability | VH | [5 empty] | 0 | 70% | 28 | 19.6 | Acceptance | Changing the deadline | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Project manager | 2 weeks | Not passed yet
[11 empty] | H |  |  |  |  | X | 0
[11 empty] | M | [5 empty] | 0
(4): Product Management | L | [5 empty] | 0
[11 empty] | VL | [5 empty] | 0
[12 empty] | VL | L | M | H | VH
Impact
8 | Active | F3R4 | Sprint 1 | Product management | Not being able to direct the employees | Lack of leadership | Schedule | Moderate | Very High | Probability | VH | [5 empty] | 0 | 40% | 28 | 11.2 | Transference | Finding a better manager | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Project manager | 4 weeks | Passed
[11 empty] | H | [5 empty] | 0
[11 empty] | M |  |  |  |  | X | 0
(4): Product Management | L | [5 empty] | 0
[11 empty] | VL | [5 empty] | 0
[12 empty] | VL | L | M | H | VH
Impact
9 | Active | F3R5 | Sprint 1 | Product management | Having a hard time to coordinate the entire team | Lack of communication | Schedule | Moderate | Very High | Probability | VH | [5 empty] | 0 | 40% | 28 | 11.2 | Transference | Finding a better manager | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Project manager | 4 weeks | Passed
[11 empty] | H | [5 empty] | 0
[11 empty] | M |  |  |  |  | X | 0
(4): Product Management | L | [5 empty] | 0
[11 empty] | VL | [5 empty] | 0
[12 empty] | VL | L | M | H | VH
Impact
10 | Dormant | F3R6 | Sprint 2 | Marketing team | Not finding clients | Not being able to showcase our strenghts to customers compared to other products on the market | Cost | Moderate | High | Probability | VH | [5 empty] | 0 | 50% | 28 | 14 | Mitigation | Trying to improve our marketing tactics by consulting another marketing firm | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Marketing team | 4 weeks | Not passed
[11 empty] | H | [5 empty] | 0
[11 empty] | M |  |  |  | X |  | 0
(4): Marketing | L | [5 empty] | 0
[11 empty] | VL | [5 empty] | 0
[12 empty] | VL | L | M | H | VH
Impact
11 | Active | F3R7 | Sprint 2 | Testing team | Bad performances of the product | Not being able to find the mistakes in how the project behaves before launching it | Quality | Very Low | Very High | Probability | VH | [5 empty] | 0 | 5% | 84 | 4.2 | Mitigation | Testing more times the product | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Testing team | 4 weeks | Not passed
H
M
(4): Testing team | L
[11 empty] | VL |  |  |  |  | X
[12 empty] | VL | L | M | H | VH
Impact